## Project Timeline & Gantt Chart
Task | Planned Date | Actual Date | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Requirements Gathering | 13/07/2026 to 19/07/2026 |  | 1 week | █
Requirement Validation | 20/07/2026 to 22/07/2026 |  | 3 days |  | █
Prototype Design | 20/07/2026 to 26/07/2026 |  | 1 week |  | █
Architecture Design | 20/07/2026 to 26/07/2026 |  | 1 week |  | █
Database Design | 23/07/2026 to 30/07/2026 |  | 1 week |  | █
Project Setup | 27/07/2026 to 31/07/2026 |  | 1 week |  |  | █
Authentication | 01/08/2026 to 05/08/2026 |  | 1 week |  |  | █
Staff Management | 06/08/2026 to 12/08/2026 |  | 1 week |  |  |  | █
Leave Request Module | 13/08/2026 to 19/08/2026 |  | 1 week |  |  |  |  | █
Approval Workflow | 20/08/2026 to 26/08/2026 |  | 1 week | [5 empty] | █
Testing | 27/08/2026 to 02/09/2026 |  | 1 week | [6 empty] | █
Deployment | 03/09/2026 to 07/09/2026 |  | 1 week | [7 empty] | █

## Milestones
Milestone | Target Date | Description | Status
Requirements Approved | 2026-07-22 | Functional and non-functional requirements documented | Planned
Prototype Approved | 2026-07-26 | Screen layouts and user navigation validated and approved before development starts | Planned
Architecture Completed | 2026-07-30 | Architecture and database design completed | Planned
MVP Completed | 2026-08-26 | Authentication , staff and leave modules completed | Planned
Testing Completed | 2026-09-02 | Unit and integration testing completed | Planned
Production Deployment | 2026-09-07 | Application hosted and available | Planned

## Sprint Planning
Sprint | Duration | Goal | Tasks | Deliverables
Sprint 1 | Week 1 | Understand the problem | Requirements gathering, user stories, acceptance criteria | Approved requirements document
Sprint 2 | Week 2 | Design solution | Architecture design, database design, UI prototype | System design and prototype approved
Sprint 3 | Week 3 | Build foundation | Solution setup, API structure, authentication, authorization | Working application foundation with login
Sprint 4 | Week 4 | Staff management | Employee CRUD, departments, roles, leave entitlement setup | Staff management module completed
Sprint 5 | Week 5-6 | Leave workflow | Leave request, approval/rejection workflow, email notifications | Complete leave management workflow
Sprint 6 | Week 7-8 | Quality & release | Unit testing, integration testing, bug fixing, deployment, documentation | Production-ready application